## actual (hidden)
Row Labels | Planned Progress | Actual Progress
2018-03-24 | 61.9048 | 46.9048
2018-03-31 | 63.9286 | 50

## Floor 01
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Progress Data - Floor 01
Room Core
Planned VS Actual Progress
Most Progressed Task Group
Current Week VS Last Week Progress
Upcoming Task Group / Subcontractors
Select Apartment
Select Task Group

## last week vs this week (hidden)
Row Labels | Current Week's Progress | Last Week's Progress
Apartment 01 | 47.9167 | 45.4167
Apartment 02 | 47.9167 | 45
Apartment 03 | 11.2004 | 11.2004
Apartment 04 | 47.9167 | 45.8333
Apartment 05 | 47.9167 | 44.375
Apartment 06 | 47.9167 | 46.8056
Apartment 07 | 47.9167 | 46.8056
Grand Total | 42.6715 | 40.7766

## most progressed task group (hidden)
Date | 2018-03-31
Row Labels | Average of Change
Commission + Inspect | 0
Flooring Installation, Kitchen Units | 0
Apartment Final Decoration | 0
M&E 1st Fix and Pod Positioning | 0
Apartment Core | 0
Room Core | 0
Main Services | 7.2222
Boarding Closure | 10.8333

## Floor 01 - Data (hidden)
TASKGROUP | TASK | PLANNED START | PLANNED END | Date | Planned Overall | Overall | APT 1 | APT 2 | APT 3 | APT 4 | APT 5 | APT 6 | APT 7 | Change
Apartment Core | Mark Wall Lines | 2017-10-28 | 2017-10-30 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-10-28 | 2017-11-03 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-11-01 | 2017-11-09 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-11-02 | 2017-11-11 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2017-11-05 | 2017-11-29 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2017-11-12 | 2017-11-18 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2017-11-19 | 2017-11-25 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2017-12-03 | 2017-12-30 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2017-12-26 | 2018-01-02 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-01-01 | 2018-01-20 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-01-04 | 2018-01-20 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-01-04 | 2018-01-20 | 2018-03-31 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-01-21 | 2018-02-10 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Mains | 2018-01-21 | 2018-02-10 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-01-21 | 2018-02-17 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 10
Main Services | Services Pipework | 2018-01-21 | 2018-02-24 | 2018-03-31 | 100 | 100 | 100 | 100 | 35 | 100 | 100 | 100 | 100 | 0
Main Services | Electrical Cabling | 2018-02-11 | 2018-02-17 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-02-18 | 2018-03-03 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 5
Main Services | AC + Utility Cupboard Cabling | 2018-02-25 | 2018-03-03 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 30
Main Services | Fire Alarm Cabling | 2018-02-18 | 2018-03-03 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 5
Main Services | Pipework Lagging | 2018-02-18 | 2018-03-03 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 15
Boarding Closure | Ceiling Firestopping | 2018-02-25 | 2018-03-10 | 2018-03-31 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 65
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-03-04 | 2018-03-11 | 2018-03-31 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Boarding | 2018-03-08 | 2018-03-19 | 2018-03-31 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-03-04 | 2018-03-24 | 2018-03-31 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Plastering/Skim Coat & Mist | 2018-03-16 | 2018-03-24 | 2018-03-31 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-03-26 | 2018-04-01 | 2018-03-31 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-04-13 | 2018-04-29 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-04-19 | 2018-05-11 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-05-13 | 2018-06-02 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-05-28 | 2018-06-08 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-05-28 | 2018-06-08 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-06-10 | 2018-06-23 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-06-14 | 2018-06-28 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-06-14 | 2018-06-28 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-06-21 | 2018-07-05 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-06-15 | 2018-07-05 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-06-15 | 2018-06-30 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-07-01 | 2018-07-14 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-06-29 | 2018-07-12 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-07-09 | 2018-07-29 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-07-18 | 2018-09-07 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Core | Mark Wall Lines | 2017-10-28 | 2017-10-30 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-10-28 | 2017-11-03 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-11-01 | 2017-11-09 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-11-02 | 2017-11-11 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2017-11-05 | 2017-11-29 | 2018-03-24 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2017-11-12 | 2017-11-18 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2017-11-19 | 2017-11-25 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2017-12-03 | 2017-12-30 | 2018-03-24 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2017-12-26 | 2018-01-02 | 2018-03-24 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-01-01 | 2018-01-20 | 2018-03-24 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-01-04 | 2018-01-20 | 2018-03-24 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-01-04 | 2018-01-20 | 2018-03-24 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-01-21 | 2018-02-10 | 2018-03-24 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Mains | 2018-01-21 | 2018-02-10 | 2018-03-24 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-01-21 | 2018-02-17 | 2018-03-24 | 100 | 90 | 95 | 95 | 0 | 100 | 50 | 100 | 100 | 0
Main Services | Services Pipework | 2018-01-21 | 2018-02-24 | 2018-03-24 | 100 | 100 | 100 | 100 | 35 | 100 | 100 | 100 | 100 | 0
Main Services | Electrical Cabling | 2018-02-11 | 2018-02-17 | 2018-03-24 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-02-18 | 2018-03-03 | 2018-03-24 | 100 | 95 | 100 | 100 | 0 | 100 | 95 | 100 | 95 | 0
Main Services | AC + Utility Cupboard Cabling | 2018-02-25 | 2018-03-03 | 2018-03-24 | 100 | 70 | 50 | 50 | 0 | 50 | 75 | 95 | 100 | 0
Main Services | Fire Alarm Cabling | 2018-02-18 | 2018-03-03 | 2018-03-24 | 100 | 95 | 75 | 100 | 0 | 100 | 100 | 100 | 100 | 0
Main Services | Pipework Lagging | 2018-02-18 | 2018-03-03 | 2018-03-24 | 100 | 85 | 75 | 95 | 0 | 75 | 75 | 100 | 100 | 0
Boarding Closure | Ceiling Firestopping | 2018-02-25 | 2018-03-10 | 2018-03-24 | 100 | 35 | 50 | 0 | 0 | 50 | 0 | 50 | 50 | 0
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-03-04 | 2018-03-11 | 2018-03-24 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Boarding | 2018-03-08 | 2018-03-19 | 2018-03-24 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-03-04 | 2018-03-24 | 2018-03-24 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Plastering/Skim Coat & Mist | 2018-03-16 | 2018-03-24 | 2018-03-24 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-03-26 | 2018-04-01 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-04-13 | 2018-04-29 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-04-19 | 2018-05-11 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-05-13 | 2018-06-02 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-05-28 | 2018-06-08 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-05-28 | 2018-06-08 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-06-10 | 2018-06-23 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-06-14 | 2018-06-28 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-06-14 | 2018-06-28 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-06-21 | 2018-07-05 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-06-15 | 2018-07-05 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-06-15 | 2018-06-30 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-07-01 | 2018-07-14 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-06-29 | 2018-07-12 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-07-09 | 2018-07-29 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-07-18 | 2018-09-07 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartments | This Week's Overall | Last Week's Overall
Apartment 01 | 47.9167 | 45.4167
Apartment 02 | 47.9167 | 45
Apartment 03 | 11.2004 | 11.2004
Apartment 04 | 47.9167 | 45.8333
Apartment 05 | 47.9167 | 44.375
Apartment 06 | 47.9167 | 46.8056
Apartment 07 | 47.9167 | 46.8056

## 2 -Actual vs planned (hidden)
Row Labels | Planned Progress | Actual Progress
2018-03-24 | 55.4286 | 55.2381
2018-03-31 | 60.3571 | 56.5476

## Floor 02
Planned VS Actual Progress
Most Progressed Task Group
Current Week VS Last Week Progress
Upcoming Task Group / Subcontractors
Select Apartment
Select Task Group
Room Core
Progress Data - Floor 02
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.

## 2 -most progressed (hidden)
Today's Date | 2018-03-31
Row Labels | Average of Change
Commission + Inspect | 0
Flooring Installation, Kitchen Units | 0
Apartment Final Decoration | 0
M&E 1st Fix and Pod Positioning | 0
Apartment Core | 0
Main Services | 0
Room Core | 0
Boarding Closure | 15.8333

## 2-last week (hidden)
Row Labels | Last Week's Progress | Current Week's Progress
Apartment 01 | 54.6429 | 57.1429
Apartment 02 | 54.0476 | 54.1667
Apartment 03 | 54.6429 | 55.8333
Apartment 04 | 18.0952 | 18.0952
Apartment 05 | 52.9762 | 52.9762
Apartment 06 | 55.3571 | 58.3333
Apartment 07 | 58.2143 | 58.3333
Apartment 08 | 57.0238 | 57.7381
Apartment 09 | 57.619 | 58.3333
Apartment 10 | 57.619 | 58.3333
Apartment 11 | 53.5714 | 58.3333
Apartment 12 | 53.5714 | 55.8333

## Floor 02 - Data (hidden)
TASKGROUP | TASK | PLANNED START | PLANNED END | Today's Date | Planned Overall | Overall | APT 1 | APT 2 | APT 3 | APT 4 | APT 5 | APT 6 | APT 7 | APT 8 | APT 9 | APT 10 | APT 11 | APT 12 | Change
Apartment Core | Mark Wall Lines | 2017-11-12 | 2017-11-16 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-11-12 | 2017-11-18 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-11-19 | 2017-11-25 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-11-17 | 2017-11-24 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2017-11-25 | 2017-12-08 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2017-11-25 | 2017-12-01 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2017-12-02 | 2017-12-08 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2017-12-16 | 2018-01-05 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2018-01-13 | 2018-01-19 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-01-20 | 2018-02-16 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-01-22 | 2018-02-12 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-01-22 | 2018-02-12 | 2018-03-31 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-02-08 | 2018-02-19 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 75 | 0
Main Services | Sprinkler Mains | 2018-02-08 | 2018-02-19 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-02-15 | 2018-02-26 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Services Pipework | 2018-02-15 | 2018-02-26 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Electrical Cabling | 2018-02-22 | 2018-03-05 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-03-01 | 2018-02-26 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | AC + Utility Cupboard Cabling | 2018-03-08 | 2018-03-12 | 2018-03-31 | 100 | 95 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 75 | 100 | 100 | 100 | 100 | 0
Main Services | Fire Alarm Cabling | 2018-03-01 | 2018-03-12 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Pipework Lagging | 2018-03-01 | 2018-03-12 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Boarding Closure | Ceiling Firestopping | 2018-03-08 | 2018-03-19 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 30 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-03-15 | 2018-03-26 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Boarding Closure | Ceiling Boarding | 2018-03-17 | 2018-03-30 | 2018-03-31 | 100 | 85 | 100 | 75 | 95 | 0 | 25 | 100 | 100 | 100 | 100 | 100 | 100 | 80 | 30
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-03-12 | 2018-04-01 | 2018-03-31 | 95 | 70 | 100 | 0 | 50 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 90 | 65
Boarding Closure | Plastering/Skim Coat & Mist | 2018-03-25 | 2018-04-09 | 2018-03-31 | 40 | 25 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-04-08 | 2018-04-12 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-04-23 | 2018-05-13 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-04-29 | 2018-05-21 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-05-25 | 2018-06-08 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-06-10 | 2018-06-18 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-06-10 | 2018-06-18 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-06-22 | 2018-07-06 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-06-24 | 2018-07-15 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-06-24 | 2018-07-08 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-07-02 | 2018-07-15 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-07-09 | 2018-07-22 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-07-09 | 2018-07-12 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-07-13 | 2018-07-19 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-07-09 | 2018-07-15 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-07-28 | 2018-08-10 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-07-31 | 2018-10-20 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Core | Mark Wall Lines | 2017-11-12 | 2017-11-16 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-11-12 | 2017-11-18 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-11-19 | 2017-11-25 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-11-17 | 2017-11-24 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2017-11-25 | 2017-12-08 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2017-11-25 | 2017-12-01 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2017-12-02 | 2017-12-08 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2017-12-16 | 2018-01-05 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2018-01-13 | 2018-01-19 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-01-20 | 2018-02-16 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-01-22 | 2018-02-12 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-01-22 | 2018-02-12 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-02-08 | 2018-02-19 | 2018-03-24 | 98 | 95 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 75 | 0
Main Services | Sprinkler Mains | 2018-02-08 | 2018-02-19 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-02-15 | 2018-02-26 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Services Pipework | 2018-02-15 | 2018-02-26 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Electrical Cabling | 2018-02-22 | 2018-03-05 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-03-01 | 2018-02-26 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | AC + Utility Cupboard Cabling | 2018-03-08 | 2018-03-12 | 2018-03-24 | 98 | 95 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 75 | 100 | 100 | 100 | 100 | 0
Main Services | Fire Alarm Cabling | 2018-03-01 | 2018-03-12 | 2018-03-24 | 99 | 95 | 95 | 95 | 95 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Pipework Lagging | 2018-03-01 | 2018-03-12 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Boarding Closure | Ceiling Firestopping | 2018-03-08 | 2018-03-19 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 30 | 100 | 100 | 100 | 95 | 100 | 100 | 100 | 100 | 0
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-03-15 | 2018-03-26 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Boarding Closure | Ceiling Boarding | 2018-03-17 | 2018-03-30 | 2018-03-24 | 74 | 75 | 100 | 75 | 75 | 0 | 25 | 50 | 95 | 100 | 95 | 95 | 50 | 50 | 0
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-03-12 | 2018-04-01 | 2018-03-24 | 41 | 40 | 0 | 0 | 25 | 0 | 0 | 75 | 100 | 75 | 75 | 75 | 0 | 25 | 0
Boarding Closure | Plastering/Skim Coat & Mist | 2018-03-25 | 2018-04-09 | 2018-03-24 | 18 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 0 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-04-08 | 2018-04-12 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-04-23 | 2018-05-13 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-04-29 | 2018-05-21 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-05-25 | 2018-06-08 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-06-10 | 2018-06-18 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-06-10 | 2018-06-18 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-06-22 | 2018-07-06 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-06-24 | 2018-07-15 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-06-24 | 2018-07-08 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-07-02 | 2018-07-15 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-07-09 | 2018-07-22 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-07-09 | 2018-07-12 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-07-13 | 2018-07-19 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-07-09 | 2018-07-15 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-07-28 | 2018-08-10 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-07-31 | 2018-10-20 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartments | Last Week Overall | This Week Overall
Apartment 01 | 54.6429 | 57.1429
Apartment 02 | 54.0476 | 54.1667
Apartment 03 | 54.6429 | 55.8333
Apartment 04 | 18.0952 | 18.0952
Apartment 05 | 52.9762 | 52.9762
Apartment 06 | 55.3571 | 58.3333
Apartment 07 | 58.2143 | 58.3333
Apartment 08 | 57.0238 | 57.7381
Apartment 09 | 57.619 | 58.3333
Apartment 10 | 57.619 | 58.3333
Apartment 11 | 53.5714 | 58.3333
Apartment 12 | 53.5714 | 55.8333

## Floor 03
Progress Data - Floor 03
Room Core
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Planned VS Actual Progress
Most Progressed Task Group
Current Week VS Last Week Progress
Upcoming Task Group / Subcontractors
Select Task Group
Select Apartment

## 3-AP (hidden)
Row Labels | Planned Progress | Actual Progress
2018-03-24 | 48.3333 | 47.9762
2018-03-31 | 52.8571 | 51.0714

## 3-MP (hidden)
Row Labels | Average of Change
Commission + Inspect | 0
Flooring Installation, Kitchen Units | 0
Apartment Final Decoration | 0
M&E 1st Fix and Pod Positioning | 0
Apartment Core | 0
Room Core | 0
Main Services | 1.6667
Boarding Closure | 8.3333

## 3-lvc (hidden)
Row Labels | Last Week's Progress | Current Week's Progress
Apartment 01 | 47.9762 | 50.9524
Apartment 02 | 49.4048 | 49.5238
Apartment 03 | 44.5238 | 51.3095
Apartment 04 | 18.2143 | 18.4524
Apartment 05 | 49.6429 | 49.881
Apartment 06 | 51.1905 | 52.2619
Apartment 07 | 49.881 | 52.2619
Apartment 08 | 49.2857 | 52.381
Apartment 09 | 46.3095 | 52.2619
Apartment 10 | 47.2619 | 52.8571
Apartment 11 | 49.4048 | 51.7857
Apartment 12 | 45.119 | 50.119

## Floor 03 - Data (hidden)
TASKGROUP | TASK | PLANNED START | PLANNED END | Today's Date | Planned Overall | Overall | APT 1 | APT 2 | APT 3 | APT 4 | APT 5 | APT 6 | APT 7 | APT 8 | APT 9 | APT 10 | APT 11 | APT 12 | Change
Apartment Core | Mark Wall Lines | 2017-11-26 | 2017-11-30 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-11-26 | 2017-12-02 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-12-03 | 2017-12-09 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-12-01 | 2017-12-08 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2017-12-09 | 2017-12-29 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2017-12-09 | 2017-12-15 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2017-12-16 | 2017-12-22 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2017-12-30 | 2018-02-03 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2018-01-22 | 2018-02-12 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-02-15 | 2018-02-26 | 2018-03-31 | 100 | 100 | 95 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-02-17 | 2018-02-24 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-02-17 | 2018-02-24 | 2018-03-31 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-03-01 | 2018-03-05 | 2018-03-31 | 100 | 95 | 100 | 100 | 100 | 0 | 95 | 100 | 100 | 100 | 95 | 95 | 95 | 70 | 0
Main Services | Sprinkler Mains | 2018-02-22 | 2018-03-12 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-03-01 | 2018-03-06 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Services Pipework | 2018-03-01 | 2018-03-19 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 5
Main Services | Electrical Cabling | 2018-03-08 | 2018-03-19 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-03-15 | 2018-03-26 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 5
Main Services | AC + Utility Cupboard Cabling | 2018-03-22 | 2018-03-26 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Fire Alarm Cabling | 2018-03-15 | 2018-03-20 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 5
Main Services | Pipework Lagging | 2018-03-15 | 2018-03-26 | 2018-03-31 | 100 | 85 | 80 | 80 | 80 | 0 | 75 | 100 | 100 | 100 | 100 | 100 | 80 | 80 | 15
Boarding Closure | Ceiling Firestopping | 2018-03-22 | 2018-04-02 | 2018-03-31 | 80 | 95 | 80 | 100 | 80 | 35 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 40
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-03-29 | 2018-04-09 | 2018-03-31 | 20 | 70 | 85 | 0 | 95 | 0 | 25 | 95 | 95 | 100 | 100 | 100 | 100 | 55 | 60
Boarding Closure | Ceiling Boarding | 2018-03-31 | 2018-04-13 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-03-27 | 2018-04-16 | 2018-03-31 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Plastering/Skim Coat & Mist | 2018-04-08 | 2018-04-23 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-04-22 | 2018-04-26 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-05-07 | 2018-05-25 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-05-13 | 2018-05-27 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-06-04 | 2018-06-25 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-06-22 | 2018-07-01 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-06-22 | 2018-07-01 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-07-05 | 2018-07-16 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-07-07 | 2018-07-27 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-07-07 | 2018-07-21 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-07-14 | 2018-07-27 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-07-21 | 2018-08-03 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-07-21 | 2018-07-22 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-07-23 | 2018-07-29 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-07-21 | 2018-07-28 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-08-09 | 2018-08-20 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-08-11 | 2018-10-30 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Core | Mark Wall Lines | 2017-11-26 | 2017-11-30 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-11-26 | 2017-12-02 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-12-03 | 2017-12-09 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-12-01 | 2017-12-08 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2017-12-09 | 2017-12-29 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2017-12-09 | 2017-12-15 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2017-12-16 | 2017-12-22 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2017-12-30 | 2018-02-03 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2018-01-22 | 2018-02-12 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-02-15 | 2018-02-26 | 2018-03-24 | 100 | 100 | 95 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-02-17 | 2018-02-24 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-02-17 | 2018-02-24 | 2018-03-24 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-03-01 | 2018-03-05 | 2018-03-24 | 100 | 95 | 100 | 100 | 100 | 0 | 95 | 100 | 100 | 100 | 95 | 95 | 95 | 70 | 0
Main Services | Sprinkler Mains | 2018-02-22 | 2018-03-12 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-03-01 | 2018-03-06 | 2018-03-24 | 100 | 100 | 95 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Services Pipework | 2018-03-01 | 2018-03-19 | 2018-03-24 | 100 | 95 | 100 | 95 | 100 | 0 | 100 | 100 | 100 | 95 | 100 | 100 | 100 | 100 | 0
Main Services | Electrical Cabling | 2018-03-08 | 2018-03-19 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-03-15 | 2018-03-26 | 2018-03-24 | 80 | 95 | 100 | 100 | 100 | 0 | 95 | 100 | 100 | 100 | 100 | 95 | 100 | 100 | 0
Main Services | AC + Utility Cupboard Cabling | 2018-03-22 | 2018-03-26 | 2018-03-24 | 50 | 100 | 100 | 100 | 95 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Fire Alarm Cabling | 2018-03-15 | 2018-03-20 | 2018-03-24 | 100 | 95 | 95 | 100 | 75 | 0 | 95 | 100 | 95 | 100 | 100 | 95 | 100 | 100 | 0
Main Services | Pipework Lagging | 2018-03-15 | 2018-03-26 | 2018-03-24 | 80 | 70 | 80 | 80 | 0 | 0 | 75 | 100 | 100 | 100 | 50 | 75 | 80 | 25 | 0
Boarding Closure | Ceiling Firestopping | 2018-03-22 | 2018-04-02 | 2018-03-24 | 20 | 55 | 50 | 100 | 0 | 25 | 100 | 75 | 100 | 75 | 0 | 25 | 100 | 0 | 0
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-03-29 | 2018-04-09 | 2018-03-24 | 0 | 10 | 0 | 0 | 0 | 0 | 25 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Boarding | 2018-03-31 | 2018-04-13 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-03-27 | 2018-04-16 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Plastering/Skim Coat & Mist | 2018-04-08 | 2018-04-23 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-04-22 | 2018-04-26 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-05-07 | 2018-05-25 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-05-13 | 2018-05-27 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-06-04 | 2018-06-25 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-06-22 | 2018-07-01 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-06-22 | 2018-07-01 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-07-05 | 2018-07-16 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-07-07 | 2018-07-27 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-07-07 | 2018-07-21 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-07-14 | 2018-07-27 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-07-21 | 2018-08-03 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-07-21 | 2018-07-22 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-07-23 | 2018-07-29 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-07-21 | 2018-07-28 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-08-09 | 2018-08-20 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-08-11 | 2018-10-30 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartments | Last Week Overall | This Week Overall
Apartment 01 | 47.9762 | 50.9524
Apartment 02 | 49.4048 | 49.5238
Apartment 03 | 44.5238 | 51.3095
Apartment 04 | 18.2143 | 18.4524
Apartment 05 | 49.6429 | 49.881
Apartment 06 | 51.1905 | 52.2619
Apartment 07 | 49.881 | 52.2619
Apartment 08 | 49.2857 | 52.381
Apartment 09 | 46.3095 | 52.2619
Apartment 10 | 47.2619 | 52.8571
Apartment 11 | 49.4048 | 51.7857
Apartment 12 | 45.119 | 50.119

## Floor 04
Progress Data - Floor 04
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Apartment Final Decoration
Planned VS Actual Progress
Most Progressed Task Group
Current Week VS Last Week Progress
Upcoming Task Group / Subcontractors
Select Task Group
Select Apartment

## 4 - pva (hidden)
Row Labels | Planned Progress | Actual Progress
2018-03-24 | 52.7381 | 46.9048
2018-03-31 | 57.8571 | 48.8095

## 4 - mp (hidden)
Row Labels | Average of Change
Commission + Inspect | 0
Flooring Installation, Kitchen Units | 0
Apartment Final Decoration | 0
M&E 1st Fix and Pod Positioning | 0
Apartment Core | 0
Room Core | 0.83333
Main Services | 1.6667
Boarding Closure | 3.75

## 4 -lvc (hidden)
Row Labels | Last Week's Progress | Current Week's Progress
Apartment 01 | 46.7857 | 48.4524
Apartment 02 | 48.3333 | 48.8095
Apartment 03 | 47.381 | 48.5714
Apartment 04 | 17.7381 | 18.5714
Apartment 05 | 47.9762 | 49.1667
Apartment 06 | 48.0952 | 49.5238
Apartment 07 | 47.2619 | 48.5714
Apartment 08 | 47.2619 | 48.5714
Apartment 09 | 44.4048 | 48.9286
Apartment 10 | 47.5 | 49.5238

## Floor 04 - Data (hidden)
TASKGROUP | TASK | PLANNED START | PLANNED END | Today's Date | Planned Overall | Overall | APT 1 | APT 2 | APT 3 | APT 4 | APT 5 | APT 6 | APT 7 | APT 8 | APT 9 | APT 10 | Change
Apartment Core | Mark Wall Lines | 2017-12-10 | 2017-12-14 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-12-10 | 2017-12-16 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-12-17 | 2017-12-23 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-12-15 | 2017-12-17 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2017-12-18 | 2017-12-31 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2017-12-18 | 2017-12-24 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2017-12-25 | 2017-12-31 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2018-01-01 | 2018-01-21 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 5 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2018-01-22 | 2018-02-11 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-02-12 | 2018-02-25 | 2018-03-31 | 100 | 100 | 95 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 5
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-02-16 | 2018-02-23 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-02-16 | 2018-02-23 | 2018-03-31 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-02-26 | 2018-03-04 | 2018-03-31 | 100 | 95 | 100 | 100 | 100 | 0 | 95 | 100 | 100 | 100 | 75 | 100 | 0
Main Services | Sprinkler Mains | 2018-02-19 | 2018-03-11 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-02-26 | 2018-03-11 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 5
Main Services | Services Pipework | 2018-02-26 | 2018-03-11 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Electrical Cabling | 2018-03-05 | 2018-03-18 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-03-12 | 2018-03-18 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | AC + Utility Cupboard Cabling | 2018-03-12 | 2018-03-18 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 5
Main Services | Fire Alarm Cabling | 2018-03-12 | 2018-03-18 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 5
Main Services | Pipework Lagging | 2018-03-12 | 2018-03-18 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 15
Boarding Closure | Ceiling Firestopping | 2018-03-19 | 2018-03-25 | 2018-03-31 | 100 | 55 | 40 | 40 | 40 | 35 | 70 | 80 | 40 | 40 | 80 | 80 | 45
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-03-23 | 2018-03-31 | 2018-03-31 | 100 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Boarding | 2018-03-25 | 2018-04-02 | 2018-03-31 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-03-22 | 2018-04-07 | 2018-03-31 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Plastering/Skim Coat & Mist | 2018-04-02 | 2018-04-08 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-04-09 | 2018-04-13 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-05-19 | 2018-06-01 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-05-25 | 2018-06-04 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-06-17 | 2018-06-25 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-06-29 | 2018-07-15 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-06-29 | 2018-07-07 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-07-15 | 2018-07-28 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-07-19 | 2018-08-06 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-07-19 | 2018-08-06 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-07-26 | 2018-08-06 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-08-02 | 2018-08-13 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-08-02 | 2018-08-03 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-08-04 | 2018-08-05 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-08-06 | 2018-08-12 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-08-16 | 2018-08-27 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-08-26 | 2018-10-09 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Core | Mark Wall Lines | 2017-12-10 | 2017-12-14 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-12-10 | 2017-12-16 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-12-17 | 2017-12-23 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-12-15 | 2017-12-17 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2017-12-18 | 2017-12-31 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2017-12-18 | 2017-12-24 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2017-12-25 | 2017-12-31 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2018-01-01 | 2018-01-21 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 5 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2018-01-22 | 2018-02-11 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-02-12 | 2018-02-25 | 2018-03-24 | 100 | 95 | 95 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-02-16 | 2018-02-23 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-02-16 | 2018-02-23 | 2018-03-24 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-02-26 | 2018-03-04 | 2018-03-24 | 100 | 95 | 100 | 100 | 100 | 0 | 95 | 100 | 100 | 100 | 75 | 100 | 0
Main Services | Sprinkler Mains | 2018-02-19 | 2018-03-11 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-02-26 | 2018-03-11 | 2018-03-24 | 100 | 95 | 100 | 100 | 100 | 0 | 100 | 100 | 95 | 95 | 95 | 100 | 0
Main Services | Services Pipework | 2018-02-26 | 2018-03-11 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Electrical Cabling | 2018-03-05 | 2018-03-18 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-03-12 | 2018-03-18 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | AC + Utility Cupboard Cabling | 2018-03-12 | 2018-03-18 | 2018-03-24 | 100 | 95 | 100 | 95 | 95 | 0 | 95 | 100 | 95 | 95 | 100 | 100 | 0
Main Services | Fire Alarm Cabling | 2018-03-12 | 2018-03-18 | 2018-03-24 | 100 | 95 | 95 | 95 | 95 | 0 | 100 | 95 | 95 | 95 | 95 | 95 | 0
Main Services | Pipework Lagging | 2018-03-12 | 2018-03-18 | 2018-03-24 | 100 | 85 | 75 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 0 | 100 | 0
Boarding Closure | Ceiling Firestopping | 2018-03-19 | 2018-03-25 | 2018-03-24 | 85 | 10 | 0 | 40 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-03-23 | 2018-03-31 | 2018-03-24 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Boarding | 2018-03-25 | 2018-04-02 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-03-22 | 2018-04-07 | 2018-03-24 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Plastering/Skim Coat & Mist | 2018-04-02 | 2018-04-08 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-04-09 | 2018-04-13 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-05-19 | 2018-06-01 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-05-25 | 2018-06-04 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-06-17 | 2018-06-25 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-06-29 | 2018-07-15 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-06-29 | 2018-07-07 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-07-15 | 2018-07-28 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-07-19 | 2018-08-06 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-07-19 | 2018-08-06 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-07-26 | 2018-08-06 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-08-02 | 2018-08-13 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-08-02 | 2018-08-03 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-08-04 | 2018-08-05 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-08-06 | 2018-08-12 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-08-16 | 2018-08-27 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-08-26 | 2018-10-09 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartments | Last Week Overall | This Week Overall
Apartment 01 | 46.7857 | 48.4524
Apartment 02 | 48.3333 | 48.8095
Apartment 03 | 47.381 | 48.5714
Apartment 04 | 17.7381 | 18.5714
Apartment 05 | 47.9762 | 49.1667
Apartment 06 | 48.0952 | 49.5238
Apartment 07 | 47.2619 | 48.5714
Apartment 08 | 47.2619 | 48.5714
Apartment 09 | 44.4048 | 48.9286
Apartment 10 | 47.5 | 49.5238

## 5 - pva (hidden)
Row Labels | Planned Progress | Actual Progress
2018-03-24 | 38.4524 | 45.4762
2018-03-31 | 48.3333 | 48.0952

## 5 - mp (hidden)
Today's Date | 2018-03-31
Row Labels | Average of Change
Commission + Inspect | 0
Flooring Installation, Kitchen Units | 0
Apartment Final Decoration | 0
M&E 1st Fix and Pod Positioning | 0
Apartment Core | 0
Room Core | 1.6667
Boarding Closure | 5.8333
Main Services | 7.7778

## 5 - lvc (hidden)
Row Labels | Last Week's Progress | Current Week's Progress
Apartment 01 | 46.1905 | 48.4524
Apartment 02 | 47.0238 | 48.5714
Apartment 03 | 47.2619 | 48.5714
Apartment 04 | 18.3333 | 18.8095
Apartment 05 | 44.5238 | 47.2619
Apartment 06 | 45.3571 | 47.9762
Apartment 07 | 44.5238 | 47.9762
Apartment 08 | 44.0476 | 47.9762
Apartment 09 | 43.9286 | 47.9762
Apartment 10 | 47.381 | 47.381

## Floor 05
Progress Data - Floor 05
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Planned VS Actual Progress
Most Progressed Task Group
Current Week VS Last Week Progress
Upcoming Task Group / Subcontractors
Select Apartments
Select Task Group
Apartment Final Decoration

## Floor 05 - Data (hidden)
TASKGROUP | TASK | PLANNED START | PLANNED END | Today's Date | Planned Overall | Overall | APT 1 | APT 2 | APT 3 | APT 4 | APT 5 | APT 6 | APT 7 | APT 8 | APT 9 | APT 10 | Change
Apartment Core | Mark Wall Lines | 2017-12-24 | 2017-12-28 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-12-24 | 2017-12-30 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-12-31 | 2018-01-06 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-12-29 | 2017-12-31 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2018-01-01 | 2018-01-14 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2018-01-01 | 2018-01-07 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2018-01-08 | 2018-01-14 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2018-01-15 | 2018-02-18 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 5 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2018-02-19 | 2018-02-25 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-02-26 | 2018-03-11 | 2018-03-31 | 100 | 100 | 95 | 100 | 100 | 0 | 95 | 100 | 100 | 100 | 100 | 100 | 5
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-03-02 | 2018-03-09 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-03-02 | 2018-03-09 | 2018-03-31 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-03-12 | 2018-03-18 | 2018-03-31 | 100 | 80 | 100 | 100 | 100 | 0 | 50 | 75 | 75 | 75 | 75 | 50 | 0
Main Services | Sprinkler Mains | 2018-03-05 | 2018-03-25 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-03-12 | 2018-03-25 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Services Pipework | 2018-03-12 | 2018-03-25 | 2018-03-31 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 5
Main Services | Electrical Cabling | 2018-03-19 | 2018-04-01 | 2018-03-31 | 90 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-03-26 | 2018-04-01 | 2018-03-31 | 85 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | AC + Utility Cupboard Cabling | 2018-03-26 | 2018-04-01 | 2018-03-31 | 85 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 5
Main Services | Fire Alarm Cabling | 2018-03-26 | 2018-04-01 | 2018-03-31 | 85 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 10
Main Services | Pipework Lagging | 2018-03-26 | 2018-04-01 | 2018-03-31 | 85 | 100 | 100 | 100 | 100 | 30 | 100 | 100 | 100 | 100 | 100 | 100 | 50
Boarding Closure | Ceiling Firestopping | 2018-04-02 | 2018-04-08 | 2018-03-31 | 0 | 40 | 40 | 40 | 40 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 35
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-04-06 | 2018-04-14 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Boarding | 2018-04-08 | 2018-04-16 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-04-05 | 2018-04-21 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Plastering/Skim Coat & Mist | 2018-04-16 | 2018-04-22 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-04-23 | 2018-04-27 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-05-28 | 2018-06-11 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-06-03 | 2018-06-16 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-06-29 | 2018-07-07 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-07-08 | 2018-07-26 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-07-08 | 2018-07-16 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-07-26 | 2018-08-06 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-07-28 | 2018-08-17 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-07-28 | 2018-08-17 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-08-04 | 2018-08-17 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-08-11 | 2018-08-24 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-08-11 | 2018-08-12 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-08-13 | 2018-08-16 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-08-17 | 2018-08-23 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-08-25 | 2018-09-07 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-09-02 | 2018-11-15 | 2018-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Core | Mark Wall Lines | 2017-12-24 | 2017-12-28 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (1st Fix) | 2017-12-24 | 2017-12-30 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Pre-Pod Firestop Stack | 2017-12-31 | 2018-01-06 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Position Pod Temporary Position | 2017-12-29 | 2017-12-31 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Party Walls Structure & Boarding | 2018-01-01 | 2018-01-14 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | M&E Stack (2nd Fix) | 2018-01-01 | 2018-01-07 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Apartment Core | Post-Pod Firestop Stack | 2018-01-08 | 2018-01-14 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 2018-01-15 | 2018-02-18 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 5 | 100 | 100 | 100 | 100 | 100 | 100 | 0
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 2018-02-19 | 2018-02-25 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Internal Walls Structure & Boarding | 2018-02-26 | 2018-03-11 | 2018-03-24 | 100 | 95 | 95 | 100 | 100 | 0 | 95 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Utility Cupboards - Decoration, Tape & Joint | 2018-03-02 | 2018-03-09 | 2018-03-24 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Room Core | Kitchen Walls - Decoration, Tape & Joint | 2018-03-02 | 2018-03-09 | 2018-03-24 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 2018-03-12 | 2018-03-18 | 2018-03-24 | 100 | 80 | 100 | 100 | 100 | 0 | 50 | 75 | 75 | 75 | 75 | 50 | 0
Main Services | Sprinkler Mains | 2018-03-05 | 2018-03-25 | 2018-03-24 | 95 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Sprinkler Heads | 2018-03-12 | 2018-03-25 | 2018-03-24 | 90 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Services Pipework | 2018-03-12 | 2018-03-25 | 2018-03-24 | 90 | 95 | 100 | 100 | 95 | 0 | 95 | 95 | 100 | 100 | 100 | 100 | 0
Main Services | Electrical Cabling | 2018-03-19 | 2018-04-01 | 2018-03-24 | 40 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | Plenums | 2018-03-26 | 2018-04-01 | 2018-03-24 | 0 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Main Services | AC + Utility Cupboard Cabling | 2018-03-26 | 2018-04-01 | 2018-03-24 | 0 | 95 | 95 | 100 | 95 | 0 | 95 | 95 | 95 | 100 | 95 | 100 | 0
Main Services | Fire Alarm Cabling | 2018-03-26 | 2018-04-01 | 2018-03-24 | 0 | 90 | 75 | 100 | 95 | 0 | 95 | 100 | 100 | 75 | 75 | 100 | 0
Main Services | Pipework Lagging | 2018-03-26 | 2018-04-01 | 2018-03-24 | 0 | 50 | 75 | 75 | 100 | 30 | 40 | 40 | 0 | 0 | 0 | 100 | 0
Boarding Closure | Ceiling Firestopping | 2018-04-02 | 2018-04-08 | 2018-03-24 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0
Boarding Closure | Ceiling Structure Grid & Bulkheads | 2018-04-06 | 2018-04-14 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Boarding | 2018-04-08 | 2018-04-16 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 2018-04-05 | 2018-04-21 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Plastering/Skim Coat & Mist | 2018-04-16 | 2018-04-22 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boarding Closure | Ceiling Decoration | 2018-04-23 | 2018-04-27 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 2018-05-28 | 2018-06-11 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 2018-06-03 | 2018-06-16 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 2018-06-29 | 2018-07-07 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 2018-07-08 | 2018-07-26 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 2018-07-08 | 2018-07-16 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 2018-07-26 | 2018-08-06 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 2018-07-28 | 2018-08-17 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 2018-07-28 | 2018-08-17 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 2018-08-04 | 2018-08-17 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 2018-08-11 | 2018-08-24 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 2018-08-11 | 2018-08-12 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 2018-08-13 | 2018-08-16 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 2018-08-17 | 2018-08-23 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 2018-08-25 | 2018-09-07 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 2018-09-02 | 2018-11-15 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apartments | Last Week Overall | This Week Overall
Apartment 01 | 46.1905 | 48.4524
Apartment 02 | 47.0238 | 48.5714
Apartment 03 | 47.2619 | 48.5714
Apartment 04 | 18.3333 | 18.8095
Apartment 05 | 44.5238 | 47.2619
Apartment 06 | 45.3571 | 47.9762
Apartment 07 | 44.5238 | 47.9762
Apartment 08 | 44.0476 | 47.9762
Apartment 09 | 43.9286 | 47.9762
Apartment 10 | 47.381 | 47.381