## task groups (hidden)
Average of Overall | Column Labels
Row Labels | Last Week's Progress | Current Week's Progress
Apartment Core | 100 | 100
Apartment Final Decoration | 0 | 0
Boarding Closure | 15 | 24.6667
Commission + Inspect | 0 | 0
Flooring Installation, Kitchen Units | 0
Flooring Installation, Kitchen Units |  | 0
M&E 1st Fix and Pod Positioning | 100 | 100
Main Services | 94.3333 | 98.8889
Room Core | 66 | 66.6667

## floors (hidden)
Row Labels | Current Week Progress | Last Week Progress
Floor 01 | 50 | 46.9048
Floor 02 | 56.5476 | 55.2381
Floor 03 | 51.0714 | 47.9762
Floor 04 | 48.8095 | 46.9048
Floor 05 | 48.0952 | 45.4762

## Actual vs planned (hidden)
Row Labels | Actual Progress | Planned Progress
Floor 01 | 50 | 64
Floor 02 | 56.5476 | 60
Floor 03 | 51.0714 | 53
Floor 04 | 48.8095 | 58
Floor 05 | 48.0952 | 48

## Summary
Progress Summary for Project - Case Study
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Actual VS Planned Progress
Last Week VS Current Week Progress
Select Task Group
Select Floor

## data (hidden)
TASKGROUP | TASK | Date | FLOOR 1 | FLOOR 2 | FLOOR 3 | FLOOR 4 | FLOOR 5 | Overall
Apartment Core | Mark Wall Lines | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Apartment Core | M&E Stack (1st Fix) | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Apartment Core | Pre-Pod Firestop Stack | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100 | Floors | Current Week | Last Week | Planned
Apartment Core | Position Pod Temporary Position | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100 | Floor 01 | 50 | 46.9048 | 64
Apartment Core | Party Walls Structure & Boarding | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100 | Floor 02 | 56.5476 | 55.2381 | 60
Apartment Core | M&E Stack (2nd Fix) | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100 | Floor 03 | 51.0714 | 47.9762 | 53
Apartment Core | Post-Pod Firestop Stack | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100 | Floor 04 | 48.8095 | 46.9048 | 58
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100 | Floor 05 | 48.0952 | 45.4762 | 48
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Room Core | Internal Walls Structure & Boarding | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Room Core | Utility Cupboards - Decoration, Tape & Joint | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Room Core | Kitchen Walls - Decoration, Tape & Joint | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 31-03-2018 | 100 | 100 | 95 | 95 | 80 | 94
Main Services | Sprinkler Mains | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Main Services | Sprinkler Heads | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Main Services | Services Pipework | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Main Services | Electrical Cabling | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Main Services | Plenums | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Main Services | AC + Utility Cupboard Cabling | 31-03-2018 | 100 | 95 | 100 | 100 | 100 | 99
Main Services | Fire Alarm Cabling | 31-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Main Services | Pipework Lagging | 31-03-2018 | 100 | 100 | 85 | 100 | 100 | 97
Boarding Closure | Ceiling Firestopping | 31-03-2018 | 100 | 100 | 95 | 55 | 40 | 78
Boarding Closure | Ceiling Structure Grid & Bulkheads | 31-03-2018 | 0 | 100 | 70 | 0 | 0 | 34
Boarding Closure | Ceiling Boarding | 31-03-2018 | 0 | 85 | 0 | 0 | 0 | 17
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 31-03-2018 | 0 | 70 | 0 | 0 | 0 | 14
Boarding Closure | Plastering/Skim Coat & Mist | 31-03-2018 | 0 | 25 | 0 | 0 | 0 | 5
Boarding Closure | Ceiling Decoration | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 31-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Core | Mark Wall Lines | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Apartment Core | M&E Stack (1st Fix) | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Apartment Core | Pre-Pod Firestop Stack | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Apartment Core | Position Pod Temporary Position | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Apartment Core | Party Walls Structure & Boarding | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Apartment Core | M&E Stack (2nd Fix) | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Apartment Core | Post-Pod Firestop Stack | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
M&E 1st Fix and Pod Positioning | Ductwork, AC & Pre-Pod Pipework | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
M&E 1st Fix and Pod Positioning | Bathroom Pod(s) Into Final Location | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Room Core | Internal Walls Structure & Boarding | 24-03-2018 | 100 | 100 | 100 | 95 | 95 | 98
Room Core | Utility Cupboards - Decoration, Tape & Joint | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Room Core | Kitchen Walls - Decoration, Tape & Joint | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Main Services | MVHR | 24-03-2018 | 100 | 95 | 95 | 95 | 80 | 93
Main Services | Sprinkler Mains | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Main Services | Sprinkler Heads | 24-03-2018 | 90 | 100 | 100 | 95 | 100 | 97
Main Services | Services Pipework | 24-03-2018 | 100 | 100 | 95 | 100 | 95 | 98
Main Services | Electrical Cabling | 24-03-2018 | 100 | 100 | 100 | 100 | 100 | 100
Main Services | Plenums | 24-03-2018 | 95 | 100 | 95 | 100 | 100 | 98
Main Services | AC + Utility Cupboard Cabling | 24-03-2018 | 70 | 95 | 100 | 95 | 95 | 91
Main Services | Fire Alarm Cabling | 24-03-2018 | 95 | 95 | 95 | 95 | 90 | 94
Main Services | Pipework Lagging | 24-03-2018 | 85 | 100 | 70 | 85 | 50 | 78
Boarding Closure | Ceiling Firestopping | 24-03-2018 | 35 | 100 | 55 | 10 | 5 | 41
Boarding Closure | Ceiling Structure Grid & Bulkheads | 24-03-2018 | 0 | 100 | 10 | 0 | 0 | 22
Boarding Closure | Ceiling Boarding | 24-03-2018 | 0 | 75 | 0 | 0 | 0 | 15
Boarding Closure | Carpentry 1st Fix (Frames, Architraves, etc.) | 24-03-2018 | 0 | 40 | 0 | 0 | 0 | 8
Boarding Closure | Plastering/Skim Coat & Mist | 24-03-2018 | 0 | 20 | 0 | 0 | 0 | 4
Boarding Closure | Ceiling Decoration | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Underfloor Heating | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Timber Flooring & Protection | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Units Installation | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Flooring Installation, Kitchen Units | Kitchen Worktop | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Wardrobe | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Doors, Frames, Skirting, Ironmongery | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Sockets, Light Switches, Data Points | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Controls + Grills | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Fire Alarm Install and Test | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Kitchen Appliances & Finals (e.g. Hobs) | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Carpet Installation | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Decoration | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Apartment Final Decoration | Final Clean | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Snag | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0
Commission + Inspect | Final Test + Commission | 24-03-2018 | 0 | 0 | 0 | 0 | 0 | 0